ALLIANCE ESTATE GROUP (AEG)

Investor & Project Management Platform — Requirements Brief for AI/Software Developer

Prepared for internal development use  |  allianceestate.com.au

# 1. Company Overview & Purpose

Alliance Estate Group (AEG) is a private real estate investment and development alliance. AEG sources, develops, and manages property projects and connects them with private investors. AEG is primarily specialised in the Australian property market, with a live portfolio of approximately 25 projects spanning residential, commercial, farming/rural land, and select international holdings (Dubai and India).

This document sets out AEG's internal process and the resulting requirements for a platform (web application, with AI-assisted tools) that will bring project management, investor relations, feasibility reporting, and communications into one connected system. It is intended for the developer/AI engineer building this platform.

# 2. Core Process Overview

AEG's operating process runs through four steps. (Licensing is handled directly by AEG and is out of scope for this platform.) The platform should mirror and support this workflow end to end.

## Step 1 — Projects

All AEG projects need to be consolidated onto one platform so they can be tracked, presented, and reported on centrally. Project categories include:

- Residential land

- Commercial land

- Farming land

- Dubai property

- Property — India

- Other property categories as they arise

Platform requirement: a project database/CRM with ~25 current projects, each with category, status (new / in development / completed), location, documents, financials, and an AEG-branded presentation view.

## Step 2 — Investors

AEG wants a dedicated investor platform/portal rather than communicating with each investor individually. Investors should be able to log in to see project updates, documents, and reports, and raise questions directly through the platform.

- Group-wide broadcast communications (updates, newsletters, project milestones)

- Self-serve access to project documents and reporting

- A query/enquiry channel investors can use to contact AEG

## Step 3 — Feasibility

For each project taken on, AEG produces a feasibility report. Existing sample feasibility reports will be provided separately as reference templates.

- Ability to generate/attach a feasibility report per project

- Standard feasibility template capturing costs, returns, timelines and risk

Sample feasibility reports to be supplied to the developer as reference formatting.

## Step 4 — Investor Exit / Unit Trust

Set-up of an investor unit trust company/structure and management of investor exit processes for completed or maturing projects.

- Unit trust entity and investor unit register

- Exit-process tracking per project (timing, distributions, sign-off)

# 3. Project Lifecycle & Delivery Process

Reference detail below is drawn from AEG's residential land subdivision / property development role scope, and should shape how the platform models a project's stages, milestones, and risk tracking.

## End-to-End Project Flow

Land Identification → Feasibility → Purchase → Survey → Planning/DA → Engineering → Council Approvals → Construction Certificate → Civil Works → Subdivision Approval & Registration → Marketing → Investor/Buyer Sales → Settlement.

The Project Manager is the single thread connecting every phase — no phase should be tracked in isolation from the others.

## Key Project Milestones

| # | Milestone | Description |
| --- | --- | --- |
| M1 | Land Settlement | Purchase completed, site secured |
| M2 | Feasibility Sign-off | Budget & returns approved by investors |
| M3 | DA Approval | Council consent granted |
| M4 | Construction Certificate | Engineering & works approved |
| M5 | Civil Works Complete | Roads, drainage, services installed |
| M6 | Subdivision Registration | New titles issued by NSW Land Registry Services |
| M7 | Lots Sold & Settled | Sales proceeds realised |

Platform requirement: each project record should carry these milestones as a status tracker (not started / in progress / complete) with target and actual dates.

## Key Responsibility Areas (Project Manager)

- Land acquisition & feasibility — zoning review, budgets, cash-flow forecasts

- Surveyor & site investigations — boundary, contour, geotechnical, environmental

- DA / planning approvals — submission, RFIs, council liaison, approvals register

- Engineering & infrastructure — roads, stormwater, sewer/water, earthworks

- Construction Certificate coordination

- Council & stakeholder management — single point of contact across all parties

- Budget & financial management — track actual vs. budget, variations, investor updates

- Project risk management (see risk register below)

- Subdivision & registration — final survey, titles, NSW Land Registry Services

- Investor & sales management — presentations, pricing strategy, contracts, settlements

## Hurdles & Risks to Manage

| Category | Example risks |
| --- | --- |
| Approvals & Regulatory | DA delays or objections; bushfire/flooding requirements; site contamination |
| Technical & Design | Unexpected site conditions; easements limiting design; engineering redesign |
| Financial & Market | Infrastructure costs exceeding estimate; interest-rate/finance risk; market conditions affecting lot sales |
| Programme & Delivery | Subdivision registration delays; consultant/contractor delays; coordination gaps |

Platform requirement: a risk register per project, tagged by category, with status and mitigation notes — feeding into the investor-facing project update.

# 4. People & Outsourced Resources

The following roles support the process above and should be represented in the platform as contact/resource records, with role-based access where relevant:

| Role | Function |
| --- | --- |
| Legal / Lawyer | Legal advisory, contracts, licensing support |
| Accountant (Corporate) | Company and project accounting |
| Project Manager (PM) | Day-to-day project delivery oversight |
| Contractors — Civil, Surveyors, Engineers | On-ground construction and survey work |
| India-based resources | Admin support and follow-up (outsourced, limited resourcing) |
| Banker | Existing banking partner working exclusively on AEG projects |

# 5. AEG Website Requirements

Website: allianceestate.com.au — to be modified as follows:

- Update the site to showcase current projects (all ~25, categorised)

- Add an "our story" / track record section — number of projects delivered in Australia, delivery locations (e.g. Adelaide), and outcomes achieved for investors

- Integrate an AI tool on the site (e.g. for investor enquiries or project matching)

- Add a customer feedback mechanism

- Provide stage-wise project update visibility for investors/visitors

# 6. Summary — Functional Requirements for the Platform

Based on the process above, the platform should provide:

- Central project database (~25+ projects) with categorisation, documents, status, milestones (M1–M7), and risk register

- Investor portal with broadcast messaging, self-serve reporting, and enquiry handling

- Feasibility report generation/attachment per project

- Unit trust / investor exit tracking

- Resource/contact directory for legal, accounting, PM, contractors, India admin, and banking partners

- Public-facing website refresh with project showcase, company track record, AI enquiry tool, and feedback capture

- Role-based access for staff, outsourced partners, and investors

# 7. Appendix — AEG Brand Launch Event (Reference)

For context, AEG is also planning a brand/product launch event. Noted here for anyone building an RSVP or event module into the platform.

- Timing: October, 2nd week (Fri / Sat / Sun) — date to be confirmed

- Venue: shortlisting large hotel venues in the Norwest, Sydney area (e.g. Novotel Sydney Norwest)

- Expected attendees: approx. 200–300

- Promotion channels: email marketing, SMS, WhatsApp, Facebook, Instagram, LinkedIn, paid promotions, SEO

- RSVP: ticketing link with barcode, RSVP tracking required

- Organiser WhatsApp group for all event organisers (internal team + external helpers)

- Digital team responsible for SEO and social media for the launch